## Contents
CPM-Critical Path Method
|  | CPM | PERT
| 1 | CPM – Algorithm | PERT – Algorithm
| 2 | CPM – Parallel Paths | PERT – Probabilities
| 3 | CPM – Crashing | PERT – Parallel Paths
Rules for Crashing a Network
| 4 | CPM – Fast Tracking | PERT – Non-critical Paths
| 5 | CPM – Resource Leveling | PERT – EMV
EMV, Crashing, Non-critical Paths
CPM Algorithm
CPM Parallel Paths
CPM Crashing
CPM Fast Tracking
CPM Resource Leveling

## 1. CPM
CPM-Critical Path Method. Algorithm
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Predecessors | --- | --- | 1 | 2 | 2 | 3,4 | 3,4,5
| Early Start | 0 | 0 | 5 | 2 | 2 | 7 | 7 | <-- ES=Max(EF of PA)
| Duration | 5 | 2 | 2 | 3 | 3 | 3 | 1
| Early Finish | 5 | 2 | 7 | 5 | 5 | 10 | 8 | <-- EF=ES+T
[7 empty] | TOC= | 10 | <-- TOC=Max(EF)
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Late Start | 0 | 2 | 5 | 4 | 6 | 7 | 9 | <-- LS=LF-T
| Duration | 5 | 2 | 2 | 3 | 3 | 3 | 1
| Late Finish | 5 | 4 | 7 | 7 | 9 | 10 | 10 | <-- LF=Min(LS of SA)
| Successors | 3 | 4,5 | 6,7 | 6,7 | 7 | --- | ---
| Slack | 0 | 2 | 0 | 2 | 4 | 0 | 2 | <-- Slack=LF-EF=LS-ES
[5 empty] | 3 |  |  |  | 7
1
6
4
2
5

## 2. CPM-PP
CPM-Critical Path Method. Algorithm
Change duration of activity 2 to 4.
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Predecessors | --- | --- | 1 | 2 | 2 | 3,4 | 3,4,5
| Early Start | 0 | 0 | 5 | 4 | 4 | 7 | 7 | <-- ES=Max(EF of PA)
| Duration | 5 | 4 | 2 | 3 | 3 | 3 | 1
| Early Finish | 5 | 4 | 7 | 7 | 7 | 10 | 8 | <-- EF=ES+T
[7 empty] | TOC= | 10 | <-- TOC=Max(EF)
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Late Start | 0 | 0 | 5 | 4 | 6 | 7 | 9 | <-- LS=LF-T
| Duration | 5 | 4 | 2 | 3 | 3 | 3 | 1
| Late Finish | 5 | 4 | 7 | 7 | 9 | 10 | 10 | <-- LF=Min(LS of SA)
| Successors | 3 | 4,5 | 6,7 | 6,7 | 7 | --- | ---
| Slack | 0 | 0 | 0 | 0 | 2 | 0 | 2 | <-- Slack=LF-EF=LS-ES
[5 empty] | 3 |  |  |  | 7
1
6
4
2
5

## 3. CPM-Crash
CPM-Critical Path Method. Crashing.
Objective: Crash project by 2. Reduce TOC=10 to TOC=8.
Crash Option 1: reduce activity 1 by 2 (i.e., from 5 to 3).
Crash Option 2: reduce activity 6 by 2 (i.e., from 3 to 1).
Crash Option 3: reduce activity 1 by 1 and activity 6 by 1 (i.e., activity 1 from 5 to 4; activity 6 from 3 to 2).
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Predecessors | --- | --- | 1 | 2 | 2 | 3,4 | 3,4,5
| Early Start | 0 | 0 | 5 | 2 | 2 | 7 | 7 | <-- ES=Max(EF of PA)
| Duration | 5 | 2 | 2 | 3 | 3 | 3 | 1
| Early Finish | 5 | 2 | 7 | 5 | 5 | 10 | 8 | <-- EF=ES+T
[7 empty] | TOC= | 10 | <-- TOC=Max(EF)
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Late Start | 0 | 2 | 5 | 4 | 6 | 7 | 9 | <-- LS=LF-T
| Duration | 5 | 2 | 2 | 3 | 3 | 3 | 1
| Late Finish | 5 | 4 | 7 | 7 | 9 | 10 | 10 | <-- LF=Min(LS of SA)
| Successors | 3 | 4,5 | 6,7 | 6,7 | 7 | --- | ---
| Slack | 0 | 2 | 0 | 2 | 4 | 0 | 2 | <-- Slack=LF-EF=LS-ES
[5 empty] | 3 |  |  |  | 7
1
6
4
2
5

## House
CPM-Critical Path Method. House Example
| Activity | A | B | C | D | E | F | G | H | I | J | K | L | M | N
| Predecessors | --- | A | A | B | D | D | D | B | C,E | G | F,I,J | K | H,G | M
| Early Start | 0 | 5 | 5 | 7 | 19 | 19 | 19 | 7 | 29 | 24 | 30 | 33 | 24 | 31 | <-- ES=Max(EF of PA)
| Duration | 5 | 2 | 6 | 12 | 10 | 9 | 5 | 9 | 1 | 2 | 3 | 9 | 7 | 8
| Early Finish | 5 | 7 | 11 | 19 | 29 | 28 | 24 | 16 | 30 | 26 | 33 | 42 | 31 | 39 | <-- EF=ES+T
|  | M: 42 | <-- TOC=Max(EF)
| Activity | A | B | C | D | E | F | G | H | I | J | K | L | M | N
| Late Start | 0 | 5 | 23 | 7 | 19 | 21 | 22 | 18 | 29 | 28 | 30 | 33 | 27 | 34 | <-- LS=LF-T
| Duration | 5 | 2 | 6 | 12 | 10 | 9 | 5 | 9 | 1 | 2 | 3 | 9 | 7 | 8
| Late Finish | 5 | 7 | 29 | 19 | 29 | 30 | 27 | 27 | 30 | 30 | 33 | 42 | 34 | 42 | <-- LF=Min(LS of SA)
| Successors | B,C | D,H | I | E,F,G | I | K | J,M | M | K | K | L | --- | N | ---
| Slack | 0 | 0 | 18 | 0 | 0 | 2 | 3 | 11 | 0 | 4 | 0 | 0 | 3 | 3 | <-- Slack=LF-EF=LS-ES