## EVA
Earned Value Analysis (EVA). Performed at the End of March | [8 empty] | EVA End of March
| Cost Baseline or Budget. |  | A 6-month, $25,000 Project | [5 empty] | Actual Cost
| Planned Value (PV) | 1 | 2 | 3 | 4 | 5 | 6 |  | 12500
| Project Activity | Jan | Feb | Mar | Apr | May | Jun | Planned Value (PV) | % Completed | Earned Value (EV)
| 1 | 1000 | 1000 |  |  |  |  | 2000 | 100% | 2000
| 2 |  | 2000 | 1000 | 2000 |  |  | 5000 | 100% | 5000
| 3 |  |  | 3000 | 2000 |  |  | 5000 | 60% | 3000
| 4 |  |  |  | 4000 | 2000 |  | 6000 | 0% | 0
| 5 |  |  |  |  | 3000 |  | 3000 | 0% | 0
| 6 |  |  |  |  | 1000 | 1000 | 2000 | 0% | 0
| 7 | [5 empty] | 2000 | 2000 | 0% | 0
| Planned Value (PV)= | 1000 | 3000 | 4000 | 8000 | 6000 | 3000 | 25000 |  | 10000
| Earned Value (EV)= | 10000 |  |  |  | ◄Earned Value from the EVA
| Actual Cost (AC)= | 12500 |  | EVA |  | ◄Actual Cost from the EVA
| Planned Value (PV)= | 8000 |  |  |  | ◄Planned Value from the EVA
| CV= | -2500 | ◄Cost Variance, CV=EV-AC=10000-12500=-2500
| SV= | 2000 | ◄Schedule Variance, CV=EV-PV=10000-8000=+2000
| CPI= | 0.8 | ◄Cost Performance Index, CV=EV/AC=10000/12500=0.8
| SPI= | 1.25 | ◄Schedule Performance Index, CV=EV/PV=10000/8000=1.25
| E[C]= | 31250 | ◄Estimated Cost at Completion,E[C]=25000/0.8=31250
| E[T]= | 4.8 | ◄Estimated Time at Completion, E[T]=6/1.25=4.8