## 1. PERT
PERT-Program Evaluation and Review Technique. Algorithm and Probabilities.
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Optimistic | 4.1 | 1.4 | 0.8 | 2.1 | 0.6 | 1.2 | 1 | <-- t1
| Most Likely | 5 | 2 | 2 | 3 | 3 | 3 | 1 | <-- t2
| Pessimistic | 7.1 | 3.2 | 6.8 | 4.5 | 4.2 | 7.2 | 1 | <-- t3
| E[T] | 5.2 | 2.1 | 2.6 | 3.1 | 2.8 | 3.4 | 1 | <-- E[T]=(t1+4t2+t3)/6
| V[T] | 0.25 | 0.09 | 1 | 0.16 | 0.36 | 1 | 0 | <-- V[T]=[ (t3-t1)/6 ]^2
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Predecessors | --- | --- | 1 | 2 | 2 | 3,4 | 3,4,5
| Early Start | 0 | 0 | 5.2 | 2.1 | 2.1 | 7.8 | 7.8 | <-- ES=Max(EF of PA)
| Duration | 5.2 | 2.1 | 2.6 | 3.1 | 2.8 | 3.4 | 1
| Early Finish | 5.2 | 2.1 | 7.8 | 5.2 | 4.9 | 11.2 | 8.8 | <-- EF=ES+T
[7 empty] | TOC= | 11.2 | <-- TOC=Max(EF)
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Late Start | 0 | 2.6 | 5.2 | 4.7 | 7.4 | 7.8 | 10.2 | <-- LS=LF-T
| Duration | 5.2 | 2.1 | 2.6 | 3.1 | 2.8 | 3.4 | 1 |  |  |  |  | 3 |  | 7
| Late Finish | 5.2 | 4.7 | 7.8 | 7.8 | 10.2 | 11.2 | 11.2 | <-- LF=Min(LS of SA) |  |  | 1
| Successors | 3 | 4,5 | 6,7 | 6,7 | 7 | --- | --- | [5 empty] | 6
| Slack | 0 | 2.6 | 0 | 2.6 | 5.3 | 0 | 2.4 | <-- Slack=LF-EF=LS-ES
[9 empty] | Sum |  |  |  | 4
| CP E[T] | 5.2 | 2.1 | 2.6 |  | 2.8 | 3.4 | 1 | 17.1
| CP V[T] | 0.25 | 0.09 | 1 |  | 0.36 | 1 | 0 | 2.7 |  |  | 2
| T | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Z= | -4.9295 | -4.3209 | -3.7123 | -3.1038 | -2.4952 | -1.8866 | -1.278 |  |  |  |  | 5
| P[TOC<T] | 4.122e-07 | 7.7689e-06 | 0.00010268 | 0.00095539 | 0.0062947 | 0.029607 | 0.10062
| A= | 1 | 2 | 3 | 4 | 5 | 6 | 7
| E[T]= | 5.2 | 2.1 | 2.6 | 3.1 | 2.8 | 3.4 | 1
| V[T]= | 0.25 | 0.09 | 1 | 0.16 | 0.36 | 1 | 0
| Path | Mean | Var | T= | 9 | 10 | 11 | 12 | 13 | 14 | 15
| 1,3,6 | 11.2 | 2.25 | P[TOC<T]= | 0.071233 | 0.21186 | 0.44696 | 0.7031 | 0.88493 | 0.96903 | 0.99435

## 3. PERT-PP
PERT-Program Evaluation and Review Technique. Parallel Paths and Non-Critical Paths
Change duration estimates of activity 5.
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Optimistic | 4.1 | 1.4 | 0.8 | 2.1 | 5.2 | 1.2 | 1 | <-- t1
| Most Likely | 5 | 2 | 2 | 3 | 7 | 3 | 1 | <-- t2
| Pessimistic | 7.1 | 3.2 | 6.8 | 4.5 | 15.4 | 7.2 | 1 | <-- t3
| E[T] | 5.2 | 2.1 | 2.6 | 3.1 | 8.1 | 3.4 | 1 | <-- E[T]=(t1+4t2+t3)/6
| V[T] | 0.25 | 0.09 | 1 | 0.16 | 2.89 | 1 | 0 | <-- V[T]=[ (t3-t1)/6 ]^2
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Predecessors | --- | --- | 1 | 2 | 2 | 3,4 | 3,4,5
| Early Start | 0 | 0 | 5.2 | 2.1 | 2.1 | 7.8 | 10.2 | <-- ES=Max(EF of PA)
| Duration | 5.2 | 2.1 | 2.6 | 3.1 | 8.1 | 3.4 | 1
| Early Finish | 5.2 | 2.1 | 7.8 | 5.2 | 10.2 | 11.2 | 11.2 | <-- EF=ES+T
[7 empty] | TOC= | 11.2 | <-- TOC=Max(EF)
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Late Start | 0 | 0 | 5.2 | 4.7 | 2.1 | 7.8 | 10.2 | <-- LS=LF-T
| Duration | 5.2 | 2.1 | 2.6 | 3.1 | 8.1 | 3.4 | 1 |  |  |  |  | 3 |  | 7
| Late Finish | 5.2 | 2.1 | 7.8 | 7.8 | 10.2 | 11.2 | 11.2 | <-- LF=Min(LS of SA) |  |  | 1
| Successors | 3 | 4,5 | 6,7 | 6,7 | 7 | --- | --- | [5 empty] | 6
| Slack | 0 | 0 | 0 | 2.6 | 0 | 0 | 0 | <-- Slack=LF-EF=LS-ES
[9 empty] | Sum |  |  |  | 4
| CP E[T] | 5.2 | 2.1 | 2.6 |  | 8.1 | 3.4 | 1 | 22.4
| CP V[T] | 0.25 | 0.09 | 1 |  | 2.89 | 1 | 0 | 5.23 |  |  | 2
| T | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Z= | -5.8594 | -5.4221 | -4.9849 | -4.5476 | -4.1103 | -3.6731 | -3.2358 |  |  |  |  | 5
| P[TOC<T] | 2.3226e-09 | 2.9445e-08 | 3.1001e-07 | 2.713e-06 | 1.9754e-05 | 0.00011983 | 0.00060652
| A= | 1 | 2 | 3 | 4 | 5 | 6 | 7
| E[T]= | 5.2 | 2.1 | 2.6 | 3.1 | 8.1 | 3.4 | 1
| V[T]= | 0.25 | 0.09 | 1 | 0.16 | 2.89 | 1 | 0
| Paths | Mean | Var | T= | 9 | 10 | 11 | 12 | 13 | 14 | 15
| 1,3,7 | 8.8 | 1.25 | P[TOC<T]= | 0.57099 | 0.85843 | 0.97545 | 0.9979 | 0.99991 | 1 | 1
| 1,3,6 | 11.2 | 2.25 | P[TOC<T]= | 0.071233 | 0.21186 | 0.44696 | 0.7031 | 0.88493 | 0.96903 | 0.99435
| 2,4,6 | 8.6 | 1.25 | P[TOC<T]= | 0.63974 | 0.89475 | 0.98409 | 0.99882 | 0.99996 | 1 | 1
| 2,4,7 | 6.2 | 0.25 | P[TOC<T]= | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 2,5,7 | 11.2 | 2.98 | P[TOC<T]= | 0.10126 | 0.24348 | 0.45388 | 0.67847 | 0.85146 | 0.9476 | 0.98614
|  |  |  | P[TOC<T]= | 0.0026347 | 0.03962 | 0.19474 | 0.47547 | 0.75339 | 0.91824 | 0.98057
| Paths | Mean | Var | T= | 9 | 10 | 11 | 12 | 13 | 14 | 15
| 1,3,6 | 11.2 | 2.25 | P[TOC<T]= | 0.071233 | 0.21186 | 0.44696 | 0.7031 | 0.88493 | 0.96903 | 0.99435
| 2,5,7 | 11.2 | 2.98 | P[TOC<T]= | 0.10126 | 0.24348 | 0.45388 | 0.67847 | 0.85146 | 0.9476 | 0.98614
|  |  |  | P[TOC<T]= | 0.0072128 | 0.051583 | 0.20287 | 0.47703 | 0.75348 | 0.91825 | 0.98057

## 5. PERT-EMV
PERT-Program Evaluation and Review Technique. Expected Monetary Value.
[8 empty] | Option 1. |  |  | Option 2.
|  | If Completed |  | Min | Max | Prob |  | Payout | EMV |  | Payout | EMV
|  | At least 2 days early |  |  | 10 | 0.21186 |  | 375 | 79.4458 |  | 275 | 58.2602
|  | 1 day early |  | 10 | 11 | 0.23511 |  | 300 | 70.5328 |  | 250 | 58.7774
|  | On time, day 12 |  | 11 | 12 | 0.25613 |  | 200 | 51.2267 |  | 200 | 51.2267
|  | 1 day late |  | 12 | 13 | 0.18183 |  | 0 | 0 |  | 150 | 27.2748
|  | At least 2 days late |  | 13 |  | 0.11507 |  | 0 | 0 |  | 40 | 4.6028
[8 empty] | Sum= | 201.2054 |  | Sum= | 200.1419
| Path | Mean | Var | T= | 9 | 10 | 11 | 12 | 13 | 14 | 15
| 1,3,6 | 11.2 | 2.25 | P[TOC<T]= | 0.071233 | 0.21186 | 0.44696 | 0.7031 | 0.88493 | 0.96903 | 0.99435
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Optimistic | 4.1 | 1.4 | 0.8 | 2.1 | 0.6 | 1.2 | 1 | <-- t1
| Most Likely | 5 | 2 | 2 | 3 | 3 | 3 | 1 | <-- t2
| Pessimistic | 7.1 | 3.2 | 6.8 | 4.5 | 4.2 | 7.2 | 1 | <-- t3
| E[T] | 5.2 | 2.1 | 2.6 | 3.1 | 2.8 | 3.4 | 1 | <-- E[T]=(t1+4t2+t3)/6
| V[T] | 0.25 | 0.09 | 1 | 0.16 | 0.36 | 1 | 0 | <-- V[T]=[ (t3-t1)/6 ]^2
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Predecessors | --- | --- | 1 | 2 | 2 | 3,4 | 3,4,5
| Early Start | 0 | 0 | 5.2 | 2.1 | 2.1 | 7.8 | 7.8 | <-- ES=Max(EF of PA)
| Duration | 5.2 | 2.1 | 2.6 | 3.1 | 2.8 | 3.4 | 1
| Early Finish | 5.2 | 2.1 | 7.8 | 5.2 | 4.9 | 11.2 | 8.8 | <-- EF=ES+T
[7 empty] | TOC= | 11.2 | <-- TOC=Max(EF)
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Late Start | 0 | 2.6 | 5.2 | 4.7 | 7.4 | 7.8 | 10.2 | <-- LS=LF-T
| Duration | 5.2 | 2.1 | 2.6 | 3.1 | 2.8 | 3.4 | 1 | [5 empty] | 3 |  | 7
| Late Finish | 5.2 | 4.7 | 7.8 | 7.8 | 10.2 | 11.2 | 11.2 | <-- LF=Min(LS of SA) |  |  |  | 1
| Successors | 3 | 4,5 | 6,7 | 6,7 | 7 | --- | --- | [6 empty] | 6
| Slack | 0 | 2.6 | 0 | 2.6 | 5.3 | 0 | 2.4 | <-- Slack=LF-EF=LS-ES
[9 empty] | Sum |  |  |  |  | 4
| CP E[T] | 5.2 | 2.1 | 2.6 |  | 2.8 | 3.4 | 1 | 17.1
| CP V[T] | 0.25 | 0.09 | 1 |  | 0.36 | 1 | 0 | 2.7 |  |  |  | 2
| T | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Z= | -4.9295 | -4.3209 | -3.7123 | -3.1038 | -2.4952 | -1.8866 | -1.278 | [5 empty] | 5
| P[TOC<T] | 4.122e-07 | 7.7689e-06 | 0.00010268 | 0.00095539 | 0.0062947 | 0.029607 | 0.10062
| A= | 1 | 2 | 3 | 4 | 5 | 6 | 7
| E[T]= | 5.2 | 2.1 | 2.6 | 3.1 | 2.8 | 3.4 | 1
| V[T]= | 0.25 | 0.09 | 1 | 0.16 | 0.36 | 1 | 0
| Path | Mean | Var | T= | 9 | 10 | 11 | 12 | 13 | 14 | 15
| 1,3,6 | 11.2 | 2.25 | P[TOC<T]= | 0.071233 | 0.21186 | 0.44696 | 0.7031 | 0.88493 | 0.96903 | 0.99435

## 5+. PERT-EMV
PERT-Program Evaluation and Review Technique. Expected Monetary Value.
| Project Probabilities | [12 empty] | Critical Path Probabilities
[5 empty] | T= | 9 | 10 | 11 | 12 | 13 | 14 | 15 |  |  | Path | Mean | Var | T= | 9 | 10 | 11 | 12 | 13 | 14 | 15
|  |  |  | Project | P[TOC<T]= | 0.02602 | 0.16272 | 0.42906 | 0.70079 | 0.88482 | 0.96902 | 0.99435 |  |  | 1,3,6 | 11.2 | 2.25 | P[TOC<T]= | 0.071233 | 0.21186 | 0.44696 | 0.7031 | 0.88493 | 0.96903 | 0.99435
[8 empty] | Option 1. |  |  | Option 2. | [9 empty] | Option 1. |  |  | Option 2.
|  |  | If Completed | Min | Max | Prob |  | Payout | EMV |  | Payout | EMV |  |  |  | If Completed | Min | Max | Prob |  | Payout | EMV |  | Payout | EMV
|  |  | At least 2 days early |  | 10 | 0.16272 |  | 375 | 61.0211 |  | 275 | 44.7488 |  |  |  | At least 2 days early |  | 10 | 0.21186 |  | 375 | 79.4458 |  | 275 | 58.2602
|  |  | 1 day early | 10 | 11 | 0.26633 |  | 300 | 79.8996 |  | 250 | 66.583 |  |  |  | 1 day early | 10 | 11 | 0.23511 |  | 300 | 70.5328 |  | 250 | 58.7774
|  |  | On time, day 12 | 11 | 12 | 0.27174 |  | 200 | 54.3475 |  | 200 | 54.3475 |  |  |  | On time, day 12 | 11 | 12 | 0.25613 |  | 200 | 51.2267 |  | 200 | 51.2267
|  |  | 1 day late | 12 | 13 | 0.18403 |  | 0 | 0 |  | 150 | 27.6038 |  |  |  | 1 day late | 12 | 13 | 0.18183 |  | 0 | 0 |  | 150 | 27.2748
|  |  | At least 2 days late | 13 |  | 0.11518 |  | 0 | 0 |  | 40 | 4.6073 |  |  |  | At least 2 days late | 13 |  | 0.11507 |  | 0 | 0 |  | 40 | 4.6028
[8 empty] | Sum= | 195.2682 |  | Sum= | 197.8904 | [8 empty] | Sum= | 201.2054 |  | Sum= | 200.1419
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Optimistic | 4.1 | 1.4 | 0.8 | 2.1 | 0.6 | 1.2 | 1 | <-- t1
| Most Likely | 5 | 2 | 2 | 3 | 3 | 3 | 1 | <-- t2
| Pessimistic | 7.1 | 3.2 | 6.8 | 4.5 | 4.2 | 7.2 | 1 | <-- t3
| E[T] | 5.2 | 2.1 | 2.6 | 3.1 | 2.8 | 3.4 | 1 | <-- E[T]=(t1+4t2+t3)/6
| V[T] | 0.25 | 0.09 | 1 | 0.16 | 0.36 | 1 | 0 | <-- V[T]=[ (t3-t1)/6 ]^2
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Predecessors | --- | --- | 1 | 2 | 2 | 3,4 | 3,4,5
| Early Start | 0 | 0 | 5.2 | 2.1 | 2.1 | 7.8 | 7.8 | <-- ES=Max(EF of PA)
| Duration | 5.2 | 2.1 | 2.6 | 3.1 | 2.8 | 3.4 | 1
| Early Finish | 5.2 | 2.1 | 7.8 | 5.2 | 4.9 | 11.2 | 8.8 | <-- EF=ES+T
[7 empty] | TOC= | 11.2 | <-- TOC=Max(EF)
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Late Start | 0 | 2.6 | 5.2 | 4.7 | 7.4 | 7.8 | 10.2 | <-- LS=LF-T
| Duration | 5.2 | 2.1 | 2.6 | 3.1 | 2.8 | 3.4 | 1 | [6 empty] | 3 |  |  |  | 7
| Late Finish | 5.2 | 4.7 | 7.8 | 7.8 | 10.2 | 11.2 | 11.2 | <-- LF=Min(LS of SA) |  |  |  | 1
| Successors | 3 | 4,5 | 6,7 | 6,7 | 7 | --- | --- | [8 empty] | 6
| Slack | 0 | 2.6 | 0 | 2.6 | 5.3 | 0 | 2.4 | <-- Slack=LF-EF=LS-ES
[9 empty] | Sum | [5 empty] | 4
| CP E[T] | 5.2 | 2.1 | 2.6 |  | 2.8 | 3.4 | 1 | 17.1
| CP V[T] | 0.25 | 0.09 | 1 |  | 0.36 | 1 | 0 | 2.7 |  |  |  | 2
| T | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Z= | -4.9295 | -4.3209 | -3.7123 | -3.1038 | -2.4952 | -1.8866 | -1.278 | [6 empty] | 5
| P[TOC<T] | 4.122e-07 | 7.7689e-06 | 0.00010268 | 0.00095539 | 0.0062947 | 0.029607 | 0.10062
| A= | 1 | 2 | 3 | 4 | 5 | 6 | 7
| E[T]= | 5.2 | 2.1 | 2.6 | 3.1 | 2.8 | 3.4 | 1
| V[T]= | 0.25 | 0.09 | 1 | 0.16 | 0.36 | 1 | 0
| Path | Mean | Var | T= | 9 | 10 | 11 | 12 | 13 | 14 | 15
| 1,3,6 | 11.2 | 2.25 | P[TOC<T]= | 0.071233 | 0.21186 | 0.44696 | 0.7031 | 0.88493 | 0.96903 | 0.99435
| Path | Mean | Var | T= | 9 | 10 | 11 | 12 | 13 | 14 | 15
| 1,3,7 | 8.8 | 1.25 | P[TOC<T]= | 0.57099 | 0.85843 | 0.97545 | 0.9979 | 0.99991 | 1 | 1
| 1,3,6 | 11.2 | 2.25 | P[TOC<T]= | 0.071233 | 0.21186 | 0.44696 | 0.7031 | 0.88493 | 0.96903 | 0.99435
| 2,4,6 | 8.6 | 1.25 | P[TOC<T]= | 0.63974 | 0.89475 | 0.98409 | 0.99882 | 0.99996 | 1 | 1
| 2,4,7 | 6.2 | 0.25 | P[TOC<T]= | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 2,5,7 | 5.9 | 0.45 | P[TOC<T]= | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  |  | P[TOC<T]= | 0.02602 | 0.16272 | 0.42906 | 0.70079 | 0.88482 | 0.96902 | 0.99435

## 7. PERT-EMV-Crash
PERT-Program Evaluation and Review Technique. Expected Monetary Value.
| Critical Path Probabilities | [12 empty] | Crash Activity to 10
[5 empty] | T= | 9 | 10 | 11 | 12 | 13 | 14 | 15 |  | Activity | 1 | 3 | 6 | None
|  |  |  | Project | P[TOC<T]= | 0.02602 | 0.16272 | 0.42906 | 0.70079 | 0.88482 | 0.96902 | 0.99435 |  | Crash | 0.23077 | 0.46154 | 0.35294 | None
[14 empty] | EMV-1 | 289.6713 | 300.3356 | 295.7577 | 195.2682
[8 empty] | Option 1. |  |  | Option 2. |  |  | EMV-2 | 241.4367 | 246.4462 | 244.5343 | 197.8904
|  |  | If Completed | Min | Max | Prob |  | Payout | EMV |  | Payout | EMV |  | TOC= | 10 | 10 | 10 | 11.2
|  |  | At least 2 days early |  | 10 | 0.16272 |  | 375 | 61.0211 |  | 275 | 44.7488
|  |  | 1 day early | 10 | 11 | 0.26633 |  | 300 | 79.8996 |  | 250 | 66.583
|  |  | On time, day 12 | 11 | 12 | 0.27174 |  | 200 | 54.3475 |  | 200 | 54.3475
|  |  | 1 day late | 12 | 13 | 0.18403 |  | 0 | 0 |  | 150 | 27.6038
|  |  | At least 2 days late | 13 |  | 0.11518 |  | 0 | 0 |  | 40 | 4.6073
[8 empty] | Sum= | 195.2682 |  | Sum= | 197.8904
[10 empty] | EMV | EMV
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7 | TOC | Option 1 | Option 2
| Slack | 0 | 2.6 | 0 | 2.6 | 5.3 | 0 | 2.4 | 11.2 | 195.2682 | 197.8904
| Critical? | Yes |  | Yes |  |  | Yes
Crash
Original Estimates
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Optimistic | 4.1 | 1.4 | 0.8 | 2.1 | 0.6 | 1.2 | 1
| Most Likely | 5 | 2 | 2 | 3 | 3 | 3 | 1
| Pessimistic | 7.1 | 3.2 | 6.8 | 4.5 | 4.2 | 7.2 | 1
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Optimistic | 4.1 | 1.4 | 0.8 | 2.1 | 0.6 | 1.2 | 1 | <-- t1
| Most Likely | 5 | 2 | 2 | 3 | 3 | 3 | 1 | <-- t2
| Pessimistic | 7.1 | 3.2 | 6.8 | 4.5 | 4.2 | 7.2 | 1 | <-- t3
| E[T] | 5.2 | 2.1 | 2.6 | 3.1 | 2.8 | 3.4 | 1 | <-- E[T]=(t1+4t2+t3)/6
| V[T] | 0.25 | 0.09 | 1 | 0.16 | 0.36 | 1 | 0 | <-- V[T]=[ (t3-t1)/6 ]^2
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Predecessors | --- | --- | 1 | 2 | 2 | 3,4 | 3,4,5
| Early Start | 0 | 0 | 5.2 | 2.1 | 2.1 | 7.8 | 7.8 | <-- ES=Max(EF of PA)
| Duration | 5.2 | 2.1 | 2.6 | 3.1 | 2.8 | 3.4 | 1
| Early Finish | 5.2 | 2.1 | 7.8 | 5.2 | 4.9 | 11.2 | 8.8 | <-- EF=ES+T
[7 empty] | TOC= | 11.2 | <-- TOC=Max(EF)
| Activity | 1 | 2 | 3 | 4 | 5 | 6 | 7
| Late Start | 0 | 2.6 | 5.2 | 4.7 | 7.4 | 7.8 | 10.2 | <-- LS=LF-T
| Duration | 5.2 | 2.1 | 2.6 | 3.1 | 2.8 | 3.4 | 1 | [5 empty] | 3 |  |  |  | 7
| Late Finish | 5.2 | 4.7 | 7.8 | 7.8 | 10.2 | 11.2 | 11.2 | <-- LF=Min(LS of SA) |  |  |  | 1
| Successors | 3 | 4,5 | 6,7 | 6,7 | 7 | --- | --- | [7 empty] | 6
| Slack | 0 | 2.6 | 0 | 2.6 | 5.3 | 0 | 2.4 | <-- Slack=LF-EF=LS-ES
[9 empty] | Sum |  |  |  |  | 4
| CP E[T] | 5.2 | 2.1 | 2.6 |  | 2.8 | 3.4 | 1 | 17.1
| CP V[T] | 0.25 | 0.09 | 1 |  | 0.36 | 1 | 0 | 2.7 |  |  |  | 2
| T | 9 | 10 | 11 | 12 | 13 | 14 | 15
| Z= | -4.9295 | -4.3209 | -3.7123 | -3.1038 | -2.4952 | -1.8866 | -1.278 | [5 empty] | 5
| P[TOC<T] | 4.122e-07 | 7.7689e-06 | 0.00010268 | 0.00095539 | 0.0062947 | 0.029607 | 0.10062
| A= | 1 | 2 | 3 | 4 | 5 | 6 | 7
| E[T]= | 5.2 | 2.1 | 2.6 | 3.1 | 2.8 | 3.4 | 1
| V[T]= | 0.25 | 0.09 | 1 | 0.16 | 0.36 | 1 | 0
| Path | Mean | Var | T= | 9 | 10 | 11 | 12 | 13 | 14 | 15
| 1,3,6 | 11.2 | 2.25 | P[TOC<T]= | 0.071233 | 0.21186 | 0.44696 | 0.7031 | 0.88493 | 0.96903 | 0.99435
| Path | Mean | Var | T= | 9 | 10 | 11 | 12 | 13 | 14 | 15
| 1,3,7 | 8.8 | 1.25 | P[TOC<T]= | 0.57099 | 0.85843 | 0.97545 | 0.9979 | 0.99991 | 1 | 1
| 1,3,6 | 11.2 | 2.25 | P[TOC<T]= | 0.071233 | 0.21186 | 0.44696 | 0.7031 | 0.88493 | 0.96903 | 0.99435
| 2,4,6 | 8.6 | 1.25 | P[TOC<T]= | 0.63974 | 0.89475 | 0.98409 | 0.99882 | 0.99996 | 1 | 1
| 2,4,7 | 6.2 | 0.25 | P[TOC<T]= | 1 | 1 | 1 | 1 | 1 | 1 | 1
| 2,5,7 | 5.9 | 0.45 | P[TOC<T]= | 1 | 1 | 1 | 1 | 1 | 1 | 1
|  |  |  | P[TOC<T]= | 0.02602 | 0.16272 | 0.42906 | 0.70079 | 0.88482 | 0.96902 | 0.99435

## 9. Summary
CPM/PERT Summary of Applications
| CPM | PERT
| Critical Path | Critical Path
| Parallel Paths | Parallel Paths
| Crashing | Non-Critical Paths
| Leveling | Crashing
EMV(Expected Monetary Value)
Extensions
EMV w/ Non-Critical Paths
EMV w/ Parallel Paths
EMV w/ Crashing
EMV w/ Non-Critical Paths & Parallel Paths & Crashing